## Sheet1
Project: | NGS N00 Limestone Piping Replacement
Location: | JEA Northside Generating Station
Project Manager: | Chuck Bursich
Technical Lead: | Kendrick Taylor
EOR: | Black & Veatch
BID FORM: The Contractor shall provide a lump sum price for replacing the existing limestone piping from the Limestone Crusher Building to the Day Bins, and from the Day Bins to the injection ports per the General Construction Specification. This bid shall be broken down by the below work items:
Item Description |  | Estimated Number of Workdays | Bid Price | Bid Unit
Phase 1 – N02 Day Bin to Furnace Injection Points
N02 Mobilization (including material and equipment staging) |  |  | 0 | LS
Line A Demolition and Disposal |  |  | 0 | LS
Line A Installation (piping, valves, and appurtenances) |  |  | 0 | LS
Line B Demolition and Disposal |  |  | 0 | LS
Line B Installation (piping, valves, and appurtenances) |  |  | 0 | LS
Line C Demolition and Disposal |  |  | 0 | LS
Line C Installation (piping, valves, and appurtenances) |  |  | 0 | LS
N02 Limestone Piping System Testing |  |  | 0 | LS
N02 Demobilization |  |  | 0 | LS
Subtotal: |  |  | 0 | LS
Phase 2 – N01 Day Bin to Furnace Injection Points
N01 Mobilization (including material and equipment staging) |  |  | 0 | LS
Line A Demolition and Disposal |  |  | 0 | LS
Line A Installation (piping, valves, and appurtenances) |  |  | 0 | LS
Line B Demolition and Disposal |  |  | 0 | LS
Line B Installation (piping, valves, and appurtenances) |  |  | 0 | LS
Line C Demolition and Disposal |  |  | 0 | LS
Line C Installation (piping, valves, and appurtenances) |  |  | 0 | LS
N01 Limestone Piping System Testing |  |  | 0 | LS
N01 Demobilization |  |  | 0 | LS
Subtotal: |  |  | 0 | LS
Phase 3 – Crusher Building to N01 & N02 Day Bins
Common Limestone Pipe Mobilization (including material and equipment staging) |  |  | 0 | LS
Line A Demolition and Disposal |  |  | 0 | LS
Line A Installation (piping, valves, and appurtenances) |  |  | 0 | LS
Line B Demolition and Disposal |  |  | 0 | LS
Line B Installation (piping, valves, and appurtenances) |  |  | 0 | LS
Line C Demolition and Disposal |  |  | 0 | LS
Line C Installation (piping, valves, and appurtenances) |  |  | 0 | LS
Common Limestone Pipe System Testing |  |  | 0 | LS
Common Limestone Pipe Demobilization |  |  | 0 | LS
Subtotal: |  |  | 0 | LS
| Total Bid (sum all subtotals): |  | 0 | LS